## Sheet1
Date: | 2021-07-13
Name | Activity
Akshay | Worked on FDM-1031 to add new currency CHF. Modified DB view to populate CHF and also may need to modify macro too. Ccontacted Samata, she said she will looked into the mail and respond back soon. Waiting here response.
Sainath | worked on External feed module implementation and testing and also worked on Fact log. Today also continue to work on the same task. And waiting for user confirmation on testing.
Siddharth | Worked with Akshay on FDM-1031 task analysis and other PFT tasks.
Srinivas | Worked with Akshay and Siddharth on FDM-1031 task analysis and other PFT tasks implementation. And also worked on FDM-1028 task as James confirmed that user can be allocated to multiple departments. Today will continue working on DB and Cube changes as suggested by Nanda.
Yasaswini | Worked on fact logic and tested and also performed few test scenarios on Fact packages. And also worked Octopus project setup and contine work on the same today. Waiting for user confirmation on Dimentsions.

## Sheet2
Date: | 2021-07-13
Name | Activity
Akshay | Worked Reconsilation count missmatch analysis on new UAT Server.
Sainath | Worked on SSIS changes related to power Apps.
Yasaswini | Analysed and validated new UAT server job status report and Reconcielation data.
Srinivas
Charvita | Yesterday, attended meeting on EBCDS queries. (Summary- We have discussed on few queries in call and they have asked us to check the columns in views on EBCDS servers). I worked on checking the views in EBCDS servers and updated to James. When coming to job issue,I have contacted srinivas for proceeding on next steps. Yesterday,I have checked the status on UAT server and copied the results.
Bhargav
Manoj

## Sheet3
Date: | 2021-08-05
Name | Activity
Akshay | Worked Reconsilation count missmatch analysis on new UAT Server.
Sainath | Worked on SSIS changes related to power Apps.
Octopus SSIS deployment done successfully.Will work change request tasks and power Apps.
Srinivas | Allocation Trigger run failed and coordinated with DBA to resolve the issue and tried to ran the allocation triggers. Peformed allocation posting. Analyzed Rec count issue in new UAT server.
Date: | 2021-08-05
Name | Activity
Charvita | Analysed EBCDS queries columns and also worked on checking the views in EBCDS servers. Regarding Job performance issue ,I have contacted srinivas for proceeding on next steps and he shared prod statistics.
Bhargav | Worked with IFRS testing team and get some inputs from them. Worked with samatha to make required changes.
Manoj | * Coordinated with Nanda on final requirements on the Pyramid data Landing * Had meeting with Pyramid team with Monica and team to discuss on finalizing the wizi pyramid requirements. * And also made sure I worked on the Pyramid data development. Initially started with the Landing area. * Also worked with James on the queries that he had pyramid data extracted the data and asked him few more requirements. * Had meeting with the testing team to discuss on the current status of the Eurobase Connection manager.