## Parameters (hidden)
|  | The following lines are used for inserting a User Story in the planning section |  |  |  | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10
---- | Plan1 |  | 0 | Sample Userstory1
---- | Plan1 |  |  | Task11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
---- | Plan1 |  |  | Task12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
---- | Plan1 |  |  | Task13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
The following line is used to insert a task
---- | Plan1 |  |  | Task11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Impediment Status
Open
Closed

## Revision History (hidden)
Revision History
1.3 | Made Sprint duration configurable; Added Impediments tracking. | C. P. Tantry | 2007-06-21
1.2 | Third team member in Col G was not displayed when filtered for a Team member. Corrected this. | C. P. Tantry | 2007-06-21
1.1 | Add User Story did not work if user story was added at the end. Added marker and note to user and corrected formulae in Remaining Hours (Cells L11 to V11 corrected.) | C. P. Tantry | 2007-06-11
1 | Release to BMS | C. P. Tantry | 2007-04-20
0.4 | Formulae for computing effort for more than 1 planning session corrected. Burndown chart sheet protected. Only available time can be entered. | C. P. Tantry | 2007-04-18
0.3 | Multiple Planning sessions can be done during the iteration. % Utilization of the team shown for the planning date. Available Hours displayed in the Burndown chart. | C. P. Tantry | 2007-03-30
0.2 | Formulae in Sprint Backlog sheet for computation of individual team member totals corrected. | C. P. Tantry | 2007-03-21
0.1 | Base version | C. P. Tantry | 2007-03-08

## Version History
|  | Iteration Backlog and Burndown Chart |  | ITS-TP035B I1.1
Company Confidential
Amendment history
Version | Date | Author | Reviewed by | Approved by | Nature of change
Issue 1.0 | 2013-04-19 | Amit Ahuja/Satya | Shalini Joshi/Nidhi Saxena | Shalini Joshi/Nidhi Saxena | First Integrated Issue
Issue 1.1 | 2013-08-01 | Raghuram G | Senthilkumar S | Thenmozhi S | Ported template in new integrated template format post merger.

## Readme
Iteration Backlog and Burndown Chart | Business Management System
Sprint/Iteration backlog and burndown template
This template can be used for sprint/iteration planning and tracking using a burndown chart. This sheet enables you to maintain more than 1 plan in an iteration. In addition this sheet enables more than one team member (max of 3 ) to sign up for a single task
The cells in green are to be entered by the user
The pending effort is entered against each task every day.
The effort spent in the previous day is entered every day for each team member.
Burndown and Burnup charts can be used to monitor progress
Sprint/Iteration Planning
The Sprint Backlog sheet can be used for planning a sprint/iteration
Enter the team member names to create the list of team members
If more than 25 names are required please insert lines before Name25
A recommended team size is 8-10 persons
Upto 3 team members can sign up for a task, each one giving an estimate for the time they will spend on the task
Enter the Sprint duration and the working day dates in the Sprint Backlog sheet
Choose the Plan Date against the Plan1 when doing the planning for the first time. For any other planning during the iteration enter against the corresponding planning occurrence.
Choose the Planning session for each row.
Choose the name of the team member against the task signed up for from the list of names.
Against each team member indicate the team member's estimate for the task
The Team Signup table in the Team Signup tab shows the total hours signed up by each team member
The Available hours for each team member should be entered against the team member for each day of the iteration.
The + or - hours are automatically determined
+ indicates spare time is available with the team member
- indicates that the team member has signed up for more hours than available
Every day the hours remaining to complete the tasks are to be entered against the tasks
The corresponding burndown chart can be used to monitor the progress
Every day the effort spent on the previous day is entered in the Team effort spent tab for each team member.
This is used to get the burnup chart.
Use of Buttons
Set Sprint Duration
Enter the Number of days in the sprint.
Exit the cell where you entered the number of days in the Sprint duration (Hit the Return or Enter key to exit)
Click on the Set Sprint Duration button. The template is reconfigured to the number of days entered. One can reduce this further but cannot increase this. A value from 5 to 30 can be chosen as the sprint duration.
Add User Story
Select a cell on any User Story row.
Click on Add User Story to insert a set of lines for a Sample User Story
The lines are added above the cell that was chosen prior to clicking the Add User Story button
Add Task
Select a cell on any Task row.
Click on Add Task to insert a set of lines for a Sample User Story
You will be asked to enter how many task lines you would like to insert
Enter the number you require. The default is 1 task row
The line(s) are added above the cell that was chosen prior to clicking the Add Task button
Show Tasks
Click this button to show all tasks for a chosen user.
Choose the 'for' field from a list of team members and click on the Show Tasks button
The cell next to it displays the total number of hours signed up by the selected user
To see for the entire team choose 'All" as the team member
Show Impediments
Click this button to go to the Impediments sheet where the impediments/barriers can be tracked
Sprint Capacity Sheet
Team to calculate their availability hours for the SPRINT before the SPRINT estimation get started. "Estimated H/ours" is compared with Sprint Capacity, detailing daywise Data given is for example only

## Team Signup
[7 empty] | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
[7 empty] | Iteration Backlog and Burndown Chart | [14 empty] | Business Management System
[5 empty] | Working day dates | 0 | 2007-03-05 | 2007-03-06 | 2007-03-07 | 2007-03-08 | 2007-03-10 | 2007-03-11 | 2007-03-12 | 2007-03-13 | 2007-03-14 | 2007-03-15 | 2007-03-16 | 2007-03-17 | 2007-03-18 | 2007-03-19 | 2007-03-20 | 2007-03-21 | 2007-03-22 | 2007-03-23 | 2007-03-24 | 2007-03-25 | 2007-03-26 | 2007-03-27 | 2007-03-28 | 2007-03-29 | 2007-03-30 | 2007-03-31 | 2007-04-01 | 2007-04-02 | 2007-04-03 | 2007-04-04 | 2007-04-05
Nbr | Team Members | Available (Hrs) | Signed up (Hrs) | Free(+)/ Over (-) | Days left | 0 | 30d | 29d | 28d | 27d | 26d | 25d | 24d | 23d | 22d | 21d | 20d | 19d | 18d | 17d | 16d | 15d | 14d | 13d | 12d | 11d | 10d | 9d | 8d | 7d | 6d | 5d | 4d | 3d | 2d | 1d | 0d
| All | 1248 | 336 | 912 | Available Hours |  | 25 | 25 | 25 | 25 | 19 | 27 | 35 | 73 | 73 | 73 | 73 | 73 | 73 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 0
1 | Name1 | 150 | 55 | 95 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
2 | Name2 | 168 | 42 | 126 |  |  | 6 | 6 | 6 | 6 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
3 | Name3 | 200 | 56 | 144 |  |  | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
4 | Name4 | 60 | 59 | 1 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
5 | Name5 | 60 | 20 | 40 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
6 | Name6 | 48 | 10 | 38 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
7 | Name7 | 96 | 20 | 76 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
8 | Name8 | 82 | 21 | 61 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
9 | Name9 | 96 | 24 | 72 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
10 | Name10 | 96 | 10 | 86 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
11 | Name11 | 96 | 15 | 81 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
12 | Name12 | 96 | 4 | 92 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
13 | Name13 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Name14 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Name15 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Name16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Name17 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Name18 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Name19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Name20 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Name21 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Name22 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Name23 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Name24 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Name25 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B5: Enter names of the team members from row 6 onwards
Note on C5: Enter the no. of available hours for each team member
Note on E5: Free(+) indicates time is available for signing up tasks Over (-) indicates signed up hrs is more than available hrs

## Sprint Backlog
[11 empty] | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
[8 empty] | Iteration Backlog and Burndown Chart | [10 empty] | Business Management System
|  |  |  | Plan # | Plan Date | Planned | Utilization |  | Sprint Duration |  | 30 | working days
|  |  |  | Plan1 | 2007-03-05 | 272 | 21.79% |  | Working day dates |  | 2007-03-05 | 2007-03-06 | 2007-03-07 | 2007-03-08 | 2007-03-10 | 2007-03-11 | 2007-03-12 | 2007-03-13 | 2007-03-14 | 2007-03-15 | 2007-03-16 | 2007-03-17 | 2007-03-18 | 2007-03-19 | 2007-03-20 | 2007-03-21 | 2007-03-22 | 2007-03-23 | 2007-03-24 | 2007-03-25 | 2007-03-26 | 2007-03-27 | 2007-03-28 | 2007-03-29 | 2007-03-30 | 2007-03-31 | 2007-04-01 | 2007-04-02 | 2007-04-03 | 2007-04-04 | 2007-04-05
|  |  |  | Plan2 | 2007-03-08 | 64 | 5.456% |  | Days left |  | 30d | 29d | 28d | 27d | 26d | 25d | 24d | 23d | 22d | 21d | 20d | 19d | 18d | 17d | 16d | 15d | 14d | 13d | 12d | 11d | 10d | 9d | 8d | 7d | 6d | 5d | 4d | 3d | 2d | 1d | 0d
|  |  |  | Plan3 |  | 0 | #N/A |  | Spent Hours |  | 25 | 50 | 75 | 100 | 119 | 146 | 181 | 254 | 327 | 400 | 473 | 546 | 619 | 656 | 693 | 730 | 767 | 804 | 841 | 878 | 915 | 952 | 989 | 1026 | 1063 | 1100 | 1137 | 1174 | 1211 | 1248 | 1248
|  |  |  | Plan4 |  | 0 | #N/A |  | Available Hours |  | 1248 | 1223 | 1198 | 1173 | 1148 | 1129 | 1102 | 1067 | 994 | 921 | 848 | 775 | 702 | 629 | 592 | 555 | 518 | 481 | 444 | 407 | 370 | 333 | 296 | 259 | 222 | 185 | 148 | 111 | 74 | 37 | 0
[5 empty] | Total planned | 336 |  |  | Ideal Hours |  | 272 | 262.9333 | 253.8667 | 308.8 | 297.363 | 285.9259 | 274.4889 | 263.0519 | 251.6148 | 240.1778 | 228.7407 | 217.3037 | 205.8667 | 194.4296 | 182.9926 | 171.5556 | 160.1185 | 148.6815 | 137.2444 | 125.8074 | 114.3704 | 102.9333 | 91.4963 | 80.0593 | 68.6222 | 57.1852 | 45.7481 | 34.3111 | 22.8741 | 11.437 | 0
| for | All |  | team member(s) |  | 336 | Hrs |  | Remaining Hours |  | 272 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names | Plan# | By | Hrs | By | Hrs | By | Hrs | User Story Hrs | User Stories
Names: ----; Plan#: Plan1 | 55 | Userstory1
-Name1-Name6-- | Plan1 | Name1 | 15 | Name6 | 10 |  |  |  | Task11 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: -Name3---; Plan#: Plan1; By: Name3; Hrs: 10 |  | Task12 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: -Name1---; Plan#: Plan1; By: Name1; Hrs: 20 |  | Task13 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: ----; Plan#: Plan1 | 45 | Userstory2
Names: -Name2---; Plan#: Plan1; By: Name2; Hrs: 15 |  | Task21 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: -Name4---; Plan#: Plan1; By: Name4; Hrs: 30 |  | Task22 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: ----; Plan#: Plan1 |  | Task23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: ----; Plan#: Plan1 | 47 | UserStory3
-Name2-Name8-- | Plan1 | Name2 | 12 | Name8 | 9 |  |  |  | Task31 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: -Name3---; Plan#: Plan1; By: Name3; Hrs: 26 |  | Task32 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: ----; Plan#: Plan1 |  | Task33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: ----; Plan#: Plan1 | 29 | Userstory4
-Name5-Name2-- | Plan1 | Name5 | 10 | Name2 | 15 |  |  |  | Task41 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: -Name4---; Plan#: Plan1; By: Name4; Hrs: 4 |  | Task42 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: ----; Plan#: Plan1 |  | Task43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: ----; Plan#: Plan1 | 50 | Userstory5
-Name7-Name11-- | Plan1 | Name7 | 20 | Name11 | 15 |  |  |  | Task51 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: -Name9---; Plan#: Plan1; By: Name9; Hrs: 15 |  | Task52 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: ----; Plan#: Plan1 |  | Task53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: ----; Plan#: Plan1 | 46 | Userstory6
-Name8-Name5-Name1- | Plan1 | Name8 | 12 | Name5 | 10 | Name1 | 20 |  | Task61 | 42 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: -Name12---; Plan#: Plan1; By: Name12; Hrs: 4 |  | Task62 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: ----; Plan#: Plan1 |  | Task63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: ----; Plan#: Plan2 | 64 | Userstory7
Names: -Name3---; Plan#: Plan2; By: Name3; Hrs: 20 |  | Task71 | 20 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: -Name4---; Plan#: Plan2; By: Name4; Hrs: 25 |  | Task72 | 25 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
-Name10-Name9-- | Plan2 | Name10 | 10 | Name9 | 9 |  |  |  | Task73 | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Do not have User Stories or tasks below this row. The Buttons 'Add User Story' or 'Add Task' inserts rows above the selected cell.
Show Tasks
Add Task
Add User Story
Set Sprint Duration
Show
Impediments
Note on E5: Upto 4 planning sessions can be done in an iteration
Note on F5: Date on which the iteration planning session is done
Note on G5: Effort signed up for in a planning session
Note on H5: Total signed up effort/available effort on the planning date expressed as a % If no plan date is chosen then it is #N/A (implies Not Applicable)
Note on L5: Enter a value from 5 to 30, hit Return, and then click on the Set Sprint Duration button. Once the duration is set to a value, it can be reset to a smaller duration only.
Note on J6: Enter the working dates for the sprint duration on this row.
Note on J9: This is a sum of the hours available for each team member during the iteration
Note on J10: Hours remaining based on even distribution across iteration
Note on C11: Enter All to display tasks for all team members or choose from the list of team members and click the Show Tasks button
Note on J11: Remaining effort in the iteration
Note on I13: This indicates the total number of hours per user story

## Team effort spent
[7 empty] | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
[5 empty] | Iteration Backlog and Burndown Chart | [15 empty] | Business Management System
[5 empty] | Total Hours spent |  | 1248
[5 empty] | Working day dates | 0 | 2007-03-05 | 2007-03-06 | 2007-03-07 | 2007-03-08 | 2007-03-10 | 2007-03-11 | 2007-03-12 | 2007-03-13 | 2007-03-14 | 2007-03-15 | 2007-03-16 | 2007-03-17 | 2007-03-18 | 2007-03-19 | 2007-03-20 | 2007-03-21 | 2007-03-22 | 2007-03-23 | 2007-03-24 | 2007-03-25 | 2007-03-26 | 2007-03-27 | 2007-03-28 | 2007-03-29 | 2007-03-30 | 2007-03-31 | 2007-04-01 | 2007-04-02 | 2007-04-03 | 2007-04-04 | 2007-04-05
Nbr | Team Members | Available (Hrs) | Signed up (Hrs) | Free(+)/ Over (-) | Days left | 0 | 30d | 29d | 28d | 27d | 26d | 25d | 24d | 23d | 22d | 21d | 20d | 19d | 18d | 17d | 16d | 15d | 14d | 13d | 12d | 11d | 10d | 9d | 8d | 7d | 6d | 5d | 4d | 3d | 2d | 1d | 0d
| All | 915 | 336 | 579 | Spent Hours |  | 25 | 25 | 25 | 25 | 19 | 27 | 35 | 73 | 73 | 73 | 73 | 73 | 73 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 0
1 | Name1 | 105 | 55 | 50 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
2 | Name2 | 114 | 42 | 72 |  |  | 6 | 6 | 6 | 6 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
3 | Name3 | 128 | 56 | 72 |  |  | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
4 | Name4 | 42 | 59 | -17 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
5 | Name5 | 42 | 20 | 22 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
6 | Name6 | 30 | 10 | 20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
7 | Name7 | 78 | 20 | 58 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
8 | Name8 | 64 | 21 | 43 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
9 | Name9 | 78 | 24 | 54 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
10 | Name10 | 78 | 10 | 68 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
11 | Name11 | 78 | 15 | 63 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
12 | Name12 | 78 | 4 | 74 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
13 | Name13 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Name14 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Name15 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Name16 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Name17 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Name18 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Name19 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Name20 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Name21 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Name22 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Name23 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Name24 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Name25 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on H3: The Value in this cell should be zero when starting the iteration. To do this all values in the Hours Spent table below should be zero.
Note on B5: Enter names of the team members from row 5 onwards
Note on C5: Enter the no. of available hours for each team member
Note on E5: Free(+) indicates time is available for signing up tasks Over (-) indicates signed up hrs is more than available hrs

## Burndown & Burnup Chart
Iteration Backlog and Burndown Chart | Business Management System

## Impediments
|  |  | Iteration Backlog and Burndown Chart |  |  |  |  | Business Management System
Impediments/Barriers
No | Date Raised | Raised by | Description | Impact | Status | Closed on | Days Open | Days to close | Remarks
1 | 2009-01-02 | [5 empty] | 1693
2 | 2009-01-02 |  |  |  |  | 2009-01-04 |  | 2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Insert rows before this line
Formulas:
Days Open = IF([Closed on]="",IF([Date Raised]="","",TODAY()-[Date Raised]),"")
Return

## Sprint Capacity
| Iteration Backlog and Burndown Chart |  |  | Business Management System
Work Days in sprint | 21 days
EAI Build team | Resource Type | Capacity (6hrs/day) | Days | Sprint Days
Team 1 | Developer | 114 | 19 | 2007-04-13
Team 2 | Developer | 114 | 19 | 2007-04-16
Team 3 | Designer/Developer | 102 | 17 | 2007-04-17
Team 4 | Designer/Developer | 108 | 18 | 2007-04-18
Team 4 | Lead Designer | 108 | 18 | 2007-04-19
Team 5 | Tester | 114 | 19 | 2007-04-20
Team 6 | Developer | 114 | 19 | 2007-04-23
Team 7 | Lead Designer | 108 | 18 | 2007-04-24
Team 8 | Designer/Developer | 84 | 14 | 2007-04-25
Team 9 | Developer | 84 | 14 | 2007-04-26
Team 10 | Developer | 84 | 14 | 2007-04-27
Team 11 | Scrum Master/Designer | 114 | 19 | 2007-04-30
| SUB TOTAL | 1134 |  | 2007-05-01
2007-05-02
Estimated Hours |  | 1206 |  | 2007-05-03
Sprint Capacity |  | 1134 |  | 2007-05-04
2007-05-07
2007-05-08
2007-05-09
2007-05-10
2007-05-11
2007-05-14