## High-Level Future Process (hidden)
OPTION 1 | [6 empty] | SO1 High Level Process changes at Q4 2019
|  | -25 | -24 | -23 | -22 | -21 | -20 | -19 | -18 | -17 | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
2019Q4 | time axis 2019-10-28 to 2020-01-07
| Non - Finance | 2019-11-13: PFT signed off / (WIZI ULR Available)
Data Validation | SYSTEM | 2019-10-28: Daily Validation Dashboard Available; 2019-11-04: Daily Validation Dashboard Available; 2019-11-11: Daily Validation Dashboard Available; 2019-11-18: Daily Validation Dashboard Available; 2019-11-25: Daily Validation Dashboard Available; 2019-12-02: Exception report of WD-1 to WD1 movements
[16 empty] | System generated reminder email to BMs | [8 empty] | System generated reminder email to BMs
| Business Managers | 2019-11-11: Signoff Premium Estimate Mth 3 (PFT); 2019-11-22: CGG Control Report Received from Dublin; 2019-11-29: Signoff Validation Dashboard / Last EPI Corrections
| Dublin Team | 2019-11-22: CGG Control Report sent by Dublin; 2019-12-02: Review Material Movements - Possible query with BMs
| MI Team | 2019-11-06: Email sent to BMs on validity of Premium Estimate Mth 3 (PFT)
Quarter End Technical Postings | SYSTEM | 2019-11-01: Posting Posting Of Gross Earned Prm Available (At first to be initiated by 'button' ) Includes UA, UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-11: Daily Overnight Posting Of Gross Earned Prm Available (At first to be initiated by 'button' ) Includes UA, UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-18: Daily Overnight Posting Of Gross Earned Prm Available (At first to be initiated by 'button' ) Includes UA, UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-22: Posting Recommended; 2019-11-25: Daily Overnight Posting Of Gross Earned Prm Available (At first to be initiated by 'button' ) Includes UA, UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-29: Posting Recommended; 2019-12-02: Overnight delta posting (Initiated by 'button')
| Dublin Team | 2019-11-01: Earned Premium Controls checked per RCM (refresh FDM report at first); 2019-11-11: Earned Premium Controls checked per RCM (refresh FDM report at first); 2019-11-18: Earned Premium Controls checked per RCM (refresh FDM report at first); 2019-11-25: Earned Premium Controls checked per RCM (refresh FDM report at first); 2019-12-02: Policy Master File Update; 2019-12-03: Other Premium Postings; 2019-12-10: Dec Dashboard Available for Upload
[15 empty] | Qtr end month Newest YOA Premium Estimate loaded to Tech Hub (1E) | 1E Estimate Analysis and post from Hub | [9 empty] | Full Year GEP Analysis Forecast / Prior Yr v Actuals Analysis REFRESHED | Full Year GEP Analysis Forecast / Prior Yr v Actuals Analysis REFRESHED

## High-Level Future Process
SO1 High Level Process changes at Q4 2019
|  | -26 | -25 | -24 | -23 | -22 | -21 | -20 | -19 | -18 | -17 | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
2019Q4 | time axis 2019-10-25 to 2020-01-07
| Non - Finance | 2019-10-25: Premium finalised for Peer Review; 2019-11-14: PFT signed off / (WIZI ULR Available)
Data Validation | SYSTEM | 2019-10-28: Daily Validation Dashboard Available; 2019-11-04: Daily Validation Dashboard Available; 2019-11-11: Daily Validation Dashboard Available; 2019-11-18: Daily Validation Dashboard Available; 2019-11-25: Daily Validation Dashboard Available; 2019-12-02: Exception report of WD-1 to WD1 movements
[6 empty] | System generated reminder email to BMs | [10 empty] | System generated reminder email to BMs | [8 empty] | System generated reminder email to BMs
| Business Managers | 2019-11-18: Signoff Premium Estimate Mth 3 (PFT); 2019-11-22: CGG Control Report Received from Dublin; 2019-11-29: Signoff Validation Dashboard / Last EPI Corrections
| Dublin Team | 2019-11-22: CGG Control Report sent by Dublin; 2019-12-02: Review Material Movements - Possible query with BMs
UW Control confirmed to CGG
| MI Team | 2019-11-14: Email sent to BMs on validity of Premium Estimate Mth 3 (PFT); 2019-11-18: New Version of PFT if required Phasing / Dec Adjt
Quarter End Technical Postings | SYSTEM | 2019-11-01: Posting Of Gross Earned Prm (At first to be initiated by 'button' ) Includes UA, UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-11: Daily Overnight Posting Of Gross Earned Prm Available (At first to be initiated by 'button' ) Includes UA, UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-22: Posting Posting Of Gross Earned Prm (At first to be initiated by 'button' ) Includes UA, UJ, UK, UM, UN, UP, UQ Process & PMF; 2019-11-29: Posting Posting Of Gross Earned Prm (At first to be initiated by 'button' ) Includes UA, UJ, UK, UM, UN, UP, UQ Process & PMF; 2019-12-02: Overnight delta posting (Initiated by 'button')
| Dublin Team | 2019-11-01: Earned Premium Controls checked per RCM (refresh FDM report at first); 2019-11-11: Earned Premium Controls checked per RCM (refresh FDM report at first); 2019-11-20: Qtr end month Newest YOA Premium Estimate loaded to Tech Hub (1E); 2019-11-22: Earned Premium Controls checked per RCM (refresh FDM report at first); 2019-11-29: Earned Premium Controls checked per RCM (refresh FDM report at first); 2019-12-02: Policy Master File Update; 2019-12-03: Other Premium Postings; 2019-12-10: Dec Dashboard Available for Upload
[7 empty] | Full Year GEP Analysis Forecast / Prior Yr v Actuals Analysis REFRESHED | [12 empty] | 1E Estimate Analysis and post from Hub |  | Full Year GEP Analysis Forecast / Prior Yr v Actuals Analysis REFRESHED |  |  |  |  | Full Year GEP Analysis Forecast / Prior Yr v Actuals Analysis REFRESHED | Full Year GEP Analysis Forecast / Prior Yr v Actuals Analysis REFRESHED

## Detailed Future Process
SO1 High Level Process changes at Q4 2019
|  | -26 | -25 | -24 | -23 | -22 | -21 | -20 | -19 | -18 | -17 | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
2019Q4 | time axis 2019-10-25 to 2020-01-07
| Non - Finance | 2019-10-25: Premium finalised for Peer Review; 2019-11-14: PFT signed off / (WIZI ULR Available)
Data Validation | SYSTEM | 2019-10-28: Daily Validation Dashboard Available; 2019-11-04: Daily Validation Dashboard Available; 2019-11-11: Daily Validation Dashboard Available; 2019-11-18: Daily Validation Dashboard Available; 2019-11-25: Daily Validation Dashboard Available; 2019-12-02: Exception report of WD-1 to WD1 movements
[6 empty] | System generated reminder email to BMs | [10 empty] | System generated reminder email to BMs | [8 empty] | System generated reminder email to BMs
| Business Managers | 2019-11-18: Signoff Premium Estimate Mth 3 (PFT); 2019-11-22: CGG Control Report Received from Dublin; 2019-11-29: Signoff Validation Dashboard / Last EPI Corrections
| Dublin Team | 2019-11-22: CGG Control Report sent by Dublin; 2019-12-02: 2nd CGG Control Report sent by Dublin; 2019-12-06: Report findings to CGG
| Project Team | 2019-11-29: Collate business sign-off and complete CGG Control; 2019-12-02: Review Material Movements - Possible query with BMs
UW Control and findings reported to CGG
| MI Team | 2019-11-14: Email sent to BMs on validity of Premium Estimate Mth 3 (PFT); 2019-11-18: New Version of PFT if required for Phasing / Dec Adjt
Business Validation | MI Team | 2019-11-04: Summary Q3 Forecast Premium Analysis Sheets Shared with Dublin
Dublin Team
Quarter End Technical Postings | SYSTEM | 2019-11-01: Gross Earned Prm available for posting Includes UA (+UB Sidecar), UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-11: Posting Of Gross Earned Prm Available Includes UA(+UB Sidecar), UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-22: Gross Earned Prm available for posting Includes UA (+UB Sidecar), UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-29: Gross Earned Prm available for posting Includes UA (+UB Sidecar), UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-12-02: Overnight delta GEP available
| Dublin Team | 2019-11-01: Premium posting; 2019-11-11: Premium posting available; 2019-11-22: Premium posting; 2019-11-29: Premium posting; 2019-12-02: Premium posting
| Dublin Team | 2019-11-01: Earned Premium Controls checked per RCM (refresh FDM post-check control reports at first); 2019-11-11: Earned Premium Controls checked per RCM (refresh FDM report at first); 2019-11-18: IF NO CHANGE Qtr end month Newest YOA Premium Estimate loaded to Tech Hub (1E); 2019-11-20: IF CHANGE TO PFT Qtr end month Newest YOA Premium Estimate loaded to Tech Hub (1E); 2019-11-22: Earned Premium Controls checked per RCM (refresh FDM post-check control reports at first); 2019-11-25: Ult Gross and RI RITC postings per FDM 9A 9B; 2019-11-29: Earned Premium Controls checked per RCM (refresh FDM post-check control reports at first); 2019-12-02: Policy Master File Update; 2019-12-03: BUSA MM Large risk cyber adjustment; 2019-12-04: Prop RI Earnings; 2019-12-05: ORC; 2019-12-10: Dec Dashboard Available for Upload
[21 empty] | RI Spend 2A | [6 empty] | AR to GL | BICI A& E Reclass | Binder / Earnings Adjt
[8 empty] | Full Year GEP Analysis Forecast / Prior Yr v Actuals Analysis REFRESHED | [9 empty] | 1E Estimate Analysis and post from Hub |  | 1E Estimate Analysis inc. 6107 and post from Hub |  | Full Year GEP Analysis Forecast / Prior Yr v Actuals Analysis REFRESHED |  |  |  |  | Full Year GEP Analysis Forecast / Prior Yr v Actuals Analysis REFRESHED | Full Year GEP Analysis Forecast / Prior Yr v Actuals Analysis REFRESHED | Gross Ult Adj
[8 empty] | Current FDM Process | Control