## High-Level Future Process (hidden)
OPTION 1 | [6 empty] | SO1 High Level Process changes at Q4 2019
|  | -25 | -24 | -23 | -22 | -21 | -20 | -19 | -18 | -17 | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
2019Q4 | time axis 2019-10-28 to 2020-01-07
| Non - Finance | 2019-11-13: PFT signed off / (WIZI ULR Available)
Data Validation | SYSTEM | 2019-10-28: Daily Validation Dashboard Available; 2019-11-04: Daily Validation Dashboard Available; 2019-11-11: Daily Validation Dashboard Available; 2019-11-18: Daily Validation Dashboard Available; 2019-11-25: Daily Validation Dashboard Available; 2019-12-02: Exception report of WD-1 to WD1 movements
[16 empty] | System generated reminder email to BMs | [8 empty] | System generated reminder email to BMs
| Business Managers | 2019-11-11: Signoff Premium Estimate Mth 3 (PFT); 2019-11-22: CGG Control Report Received from Dublin; 2019-11-29: Signoff Validation Dashboard / Last EPI Corrections
| Dublin Team | 2019-11-22: CGG Control Report sent by Dublin; 2019-12-02: Review Material Movements - Possible query with BMs
| MI Team | 2019-11-06: Email sent to BMs on validity of Premium Estimate Mth 3 (PFT)
Quarter End Technical Postings | SYSTEM | 2019-11-01: Posting Posting Of Gross Earned Prm Available (At first to be initiated by 'button' ) Includes UA, UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-11: Daily Overnight Posting Of Gross Earned Prm Available (At first to be initiated by 'button' ) Includes UA, UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-18: Daily Overnight Posting Of Gross Earned Prm Available (At first to be initiated by 'button' ) Includes UA, UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-22: Posting Recommended; 2019-11-25: Daily Overnight Posting Of Gross Earned Prm Available (At first to be initiated by 'button' ) Includes UA, UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-29: Posting Recommended; 2019-12-02: Overnight delta posting (Initiated by 'button')
| Dublin Team | 2019-11-01: Earned Premium Controls checked per RCM (refresh FDM report at first); 2019-11-11: Earned Premium Controls checked per RCM (refresh FDM report at first); 2019-11-18: Earned Premium Controls checked per RCM (refresh FDM report at first); 2019-11-25: Earned Premium Controls checked per RCM (refresh FDM report at first); 2019-12-02: Policy Master File Update; 2019-12-03: Other Premium Postings; 2019-12-10: Dec Dashboard Available for Upload
[15 empty] | Qtr end month Newest YOA Premium Estimate loaded to Tech Hub (1E) | 1E Estimate Analysis and post from Hub | [9 empty] | Full Year GEP Analysis Forecast / Prior Yr v Actuals Analysis REFRESHED | Full Year GEP Analysis Forecast / Prior Yr v Actuals Analysis REFRESHED

## Detailed Q4 Process (Summary)
KEY |  | Existing Timetable |  | SO1 Timetable |  | Future process
WD Count | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
2019Q4 | 2019-11-27 | 2019-11-28 | 2019-11-29 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06 | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-23 | 2019-12-24 | 2019-12-27 | 2019-12-30 | 2019-12-31 | 2020-01-02 | 2020-01-03
| Current Timetable | EPI Cut
EPI loading
Top up to ultimate
Earnings and binder adjustments
5623 premium postings (gross)
RI journals (Quota Share RI)
RI journals inc ORC/ earnings
Cut of qtr FX rates - Agresso*
WIZI November Net Close*
WIZI Signings / LPSO
Gross/Net ULR's
Premium Reconciliations
* Process outside of our control

## Detailed Q4 Process - Current
| KEY | Process | Current FDM Process | Control | Posting |  |  | SO1 Process changes at Q4 2019
| WD Count | -26 | -25 | -24 | -23 | -22 | -21 | -20 | -19 | -18 | -17 | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
2019Q4 | time axis 2019-10-25 to 2020-01-03
Outside Finance Dependancy | Non - Finance | 2019-10-25: Premium finalised for Peer Review; 2019-11-14: PFT signed off / (WIZI ULR Available); 2019-12-10: WIZI November Net Cube Closure
[16 empty] | October Flash approved in UW Committee | [20 empty] | November Flash approved in UW Committee
Data Validation | SYSTEM | 2019-10-28: Daily Validation Dashboard Available; 2019-11-04: Daily Validation Dashboard Available; 2019-11-11: Daily Validation Dashboard Available; 2019-11-18: Daily Validation Dashboard Available; 2019-11-25: Daily Validation Dashboard Available; 2019-12-02: Daily Validation Dashboard Available; 2019-12-09: Daily Validation Dashboard Available; 2019-12-16: Daily Validation Dashboard Available; 2019-12-23: Daily Validation Dashboard Available; 2019-12-30: Daily Validation Dashboard Available
[6 empty] | System generated reminder email to BMs | [8 empty] | System generated reminder email to BMs | [10 empty] | System generated reminder email to BMs |  | Exception report of WD-1 to WD1 movements
| Business Managers | 2019-11-18: Signoff Premium Estimate Mth 3 (PFT); 2019-11-22: CGG Control Report sent to Dublin; 2019-11-29: Signoff Validation Dashboard / Last EPI Corrections
| Dublin Team | 2019-11-22: CGG Control Report sent by Dublin; 2019-12-02: 2nd CGG Control Report sent by Dublin; 2019-12-06: Report findings to CGG
| Project Team | 2019-11-29: Collate business sign-off and complete CGG Control; 2019-12-02: Review Material Movements - Possible query with BMs
UW Control and findings reported to CGG
| MI Team | 2019-11-13: PFT v WIZI Ultimate Prm Reconciliation; 2019-11-14: Email sent to BMs on validity of Premium Estimate Mth 3 (PFT); 2019-11-18: New Version of PFT if required for Phasing / Dec Adjt. Q4 tactical solution - Manual 1E Journal
Business Validation | Dublin Team
| Project Team | 2019-11-29: October/November Actuals compared to October /November PFT using Tech Hub; 2019-12-09: Monitor EPI in December tracked against PFT - discrepancies in writing patterns are investigated. Material variances are fed back to BMs to review and action, and any non-actioned variances are escalated to Finance management.
| MI Team | 2019-11-07: Summary Q3 Forecast Premium Analysis Sheets Shared with Dublin
[7 empty] | Process started for October Flash | Flash distributed to BMs for commentary and Finance review meeting held with BPs |  | Flash submitted to the UW committee | YTD 31/10 GEP Analysis Forecast v Actuals Analysis |  |  |  | Flash EPI refresh done to give most up to date view | [7 empty] | YTD 31/10 GEP Analysis Forecast v Actuals Analysis |  |  |  |  | Process started for November Flash | Flash distributed to BMs for commentary and Finance review meeting held with BPs |  | Flash submitted to the UW committee |  |  |  |  | Flash EPI refresh done to give most up to date view
General Ledger Postings & Reconciliations | SYSTEM | 2019-10-28: Gross Earned Prm available for posting Includes UA (+UB Sidecar), UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-04: Gross Earned Prm available for posting Includes UA (+UB Sidecar), UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-11: Gross Earned Prm available for posting Includes UA (+UB Sidecar), UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-18: Gross Earned Prm available for posting Includes UA (+UB Sidecar), UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-25: Gross Earned Prm available for posting Includes UA (+UB Sidecar), UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-12-02: Overnight delta GEP available
| FDM Support | 2019-11-01: Premium posting; 2019-11-15: GEP Premium posting + 1E posting; 2019-11-29: Premium posting; 2019-12-02: Premium posting
| Dublin Team | 2019-11-20: 1E Estimate Premium posting; 2019-11-22: Premium posting; 2019-12-02: Large Loss RI Premium (1D 2D); 2019-12-04: ORC; 2019-12-31: Final Period Postings; 2020-01-03: 2nd Cut Posting if material
[7 empty] | Earned Premium Controls checked per RCM (refresh FDM post-check control reports at first) | [9 empty] | Earned Premium Controls checked per RCM (refresh FDM post-check control reports at first) | IF NO CHANGE Qtr end month Newest YOA Premium Estimate loaded to Tech Hub (1E) |  | IF CHANGE TO PFT - tactical solution posting 1E adjt journal to Agresso. Future Solution -[Qtr end month Newest YOA Premium Estimate loaded to Tech Hub (1E)] |  | Earned Premium Controls checked per RCM (refresh FDM post-check control reports at first) | Ult Gross and RI RITC postings per FDM (9A 9B) |  |  |  | Earned Premium Controls checked per RCM (refresh FDM post-check control reports at first) | Policy Master File Update | BUSA MM Cyber Large Risk Adj | QS RI | Complete Reconciliations |  |  | Dec Dashboard Available for Upload | Complete and upload Reconciliations to Dashboard | [12 empty] | Dec Dashboard Finalised | Redo Dec Rec?
[17 empty] | US BUSA BICI Premium Movements -September / October |  |  |  | RI Spend (2A) | RI Earnings - Non QS RAD & LOD (3G 3H) | [5 empty] | AR to GL | 5623 QS | Binder / Earnings Adjt | IPT Write-off |  |  | WIZI / LPSO Signings |  | ULR | [11 empty] | 2nd Cut Premium Process - REVIEW and SIGN OFF
[8 empty] | YTD 31/10 GEP Analysis Prior Yr v Actuals Analysis | [9 empty] | 1E Estimate Analysis inc. 6107 |  | 1E Estimate Analysis inc. 6107 |  | Full Year GEP Analysis Prior Yr v Actuals Analysis REFRESHED |  |  |  |  | Full Year GEP Analysis Forecast / Prior Yr v Actuals Analysis REFRESHED | Full Year GEP Analysis Forecast / Prior Yr v Actuals Analysis REFRESHED | Gross Ult Adj | RI Earnings
| KEY | 2019-10-25: Process; 2019-10-28: Current FDM Process; 2019-10-29: Control; 2019-10-30: Posting
[25 empty] | Current Timetable | EPI Cut
EPI loading
[22 empty] | Existing Timetable |  |  |  | Top up to ultimate
[22 empty] | SO1 Timetable |  |  |  | Earnings and binder adjustments
5623 premium postings (gross)
RI journals (Quota Share RI)
RI journals inc ORC/ earnings
Cut of qtr FX rates - Agresso
WIZI November Net Close
WIZI Signings / LPSO
Gross/Net ULR's
Sign-off by Management if change to PFT required.

## Detailed Q4 Process - New
| KEY | Process | Current FDM Process | Control | Posting |  |  | SO1 Process changes at Q4 2019
| WD Count | -26 | -25 | -24 | -23 | -22 | -21 | -20 | -19 | -18 | -17 | -16 | -15 | -14 | -13 | -12 | -11 | -10 | -9 | -8 | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
2019Q4 | time axis 2019-10-25 to 2020-01-03
Outside Finance Dependancy | Non - Finance | 2019-10-25: Premium finalised for Peer Review; 2019-11-14: PFT signed off / (WIZI ULR Available); 2019-12-10: WIZI November Net Cube Closure
[16 empty] | October Flash approved in UW Committee | [20 empty] | November Flash approved in UW Committee
Data Validation | SYSTEM | 2019-10-28: Daily Validation Dashboard Available; 2019-11-04: Daily Validation Dashboard Available; 2019-11-11: Daily Validation Dashboard Available; 2019-11-18: Daily Validation Dashboard Available; 2019-11-25: Daily Validation Dashboard Available; 2019-12-02: Daily Validation Dashboard Available; 2019-12-09: Daily Validation Dashboard Available; 2019-12-16: Daily Validation Dashboard Available; 2019-12-23: Daily Validation Dashboard Available; 2019-12-30: Daily Validation Dashboard Available
[6 empty] | System generated reminder email to BMs | [8 empty] | System generated reminder email to BMs | [12 empty] | Exception report of WD-1 to WD1 movements
| Business Managers | 2019-11-18: Signoff Premium Estimate Mth 3 (PFT); 2019-11-29: Signoff Validation Dashboard / Last EPI Corrections
Dublin Team
| Project Team | 2019-11-29: Collate business sign-off and complete CGG Control; 2019-12-02: Review Material Movements - Possible query with BMs
UW Control and findings reported to CGG
| MI Team | 2019-11-13: PFT v WIZI Ultimate Prm Reconciliation; 2019-11-14: Email sent to BMs on validity of Premium Estimate Mth 3 (PFT); 2019-11-18: New Version of PFT if required for Phasing / Dec Adjt. Q4 tactical solution - Manual 1E Journal
Business Validation | Dublin Team
| Project Team | 2019-11-29: October/November Actuals compared to October /November PFT using Tech Hub; 2019-12-09: Monitor EPI in December tracked against PFT - discrepancies in writing patterns are investigated. Material variances are fed back to BMs to review and action, and any non-actioned variances are escalated to Finance management.
| MI Team | 2019-11-07: Summary Q3 Forecast Premium Analysis Sheets Shared with Dublin
[7 empty] | Process started for October Flash | Flash distributed to BMs for commentary and Finance review meeting held with BPs |  | Flash submitted to the UW committee | YTD 31/10 GEP Analysis Forecast v Actuals Analysis |  |  |  | Flash EPI refresh done to give most up to date view | [7 empty] | YTD 31/10 GEP Analysis Forecast v Actuals Analysis |  |  |  |  | Process started for November Flash | Flash distributed to BMs for commentary and Finance review meeting held with BPs |  | Flash submitted to the UW committee |  |  |  |  | Flash EPI refresh done to give most up to date view
General Ledger Postings & Reconciliations | SYSTEM | 2019-10-28: Gross Earned Prm available for posting Includes UA (+UB Sidecar), UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-04: Gross Earned Prm available for posting Includes UA (+UB Sidecar), UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-11: Gross Earned Prm available for posting Includes UA (+UB Sidecar), UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-18: Gross Earned Prm available for posting Includes UA (+UB Sidecar), UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-11-25: Gross Earned Prm available for posting Includes UA (+UB Sidecar), UJ, UK, UM, UN, UP, UQ Process & Policy Master File; 2019-12-02: Overnight delta GEP available
| FDM Support | 2019-11-01: Premium posting; 2019-11-15: GEP Premium posting + 1E posting; 2019-11-29: Premium posting; 2019-12-02: Premium posting
| Dublin Team | 2019-11-20: 1E Estimate Premium posting; 2019-11-22: Premium posting; 2019-12-02: Large Loss RI Premium (1D 2D); 2019-12-04: ORC; 2019-12-31: Final Period Postings; 2020-01-03: 2nd Cut Posting if material
[7 empty] | Earned Premium Controls checked per RCM (refresh FDM post-check control reports at first) | [9 empty] | Earned Premium Controls checked per RCM (refresh FDM post-check control reports at first) | IF NO CHANGE Qtr end month Newest YOA Premium Estimate loaded to Tech Hub (1E) |  | IF CHANGE TO PFT - tactical solution posting 1E adjt journal to Agresso. Future Solution -[Qtr end month Newest YOA Premium Estimate loaded to Tech Hub (1E)] |  | Earned Premium Controls checked per RCM (refresh FDM post-check control reports at first) | Ult Gross and RI RITC postings per FDM (9A 9B) |  |  |  | Earned Premium Controls checked per RCM (refresh FDM post-check control reports at first) |  | BUSA MM Cyber Large Risk Adj | QS RI | Complete Reconciliations |  |  | Dec Dashboard Available for Upload | Complete and upload Reconciliations to Dashboard | [12 empty] | Dec Dashboard Finalised | Redo Dec Rec?
[21 empty] | RI Spend (2A) | RI Earnings - Non QS RAD & LOD (3G 3H) | [5 empty] | AR to GL | 5623 QS |  | IPT Write-off |  |  | WIZI / LPSO Signings |  | ULR | [11 empty] | 2nd Cut Premium Process - REVIEW and SIGN OFF
[8 empty] | YTD 31/10 GEP Analysis Prior Yr v Actuals Analysis | [9 empty] | 1E Estimate Analysis inc. 6107 |  | 1E Estimate Analysis inc. 6107 |  | Full Year GEP Analysis Prior Yr v Actuals Analysis REFRESHED |  |  |  |  | Full Year GEP Analysis Forecast / Prior Yr v Actuals Analysis REFRESHED | Full Year GEP Analysis Forecast / Prior Yr v Actuals Analysis REFRESHED | Gross Ult Adj | RI Earnings
| KEY | 2019-10-25: Process; 2019-10-28: Current FDM Process; 2019-10-29: Control; 2019-10-30: Posting
[25 empty] | Current Timetable | EPI Cut
EPI loading
[22 empty] | Existing Timetable |  |  |  | Top up to ultimate
[22 empty] | SO1 Timetable |  |  |  | Earnings and binder adjustments
5623 premium postings (gross)
RI journals (Quota Share RI)
RI journals inc ORC/ earnings
Cut of qtr FX rates - Agresso
WIZI November Net Close
WIZI Signings / LPSO
Gross/Net ULR's
Sign-off by Management if change to PFT required.

## Detailed Day to day
SO1 Process changes at Q4 2019
|  | Who ? | Process | Detail
-25 | 2019-10-28
-24 | 2019-10-29 | [6 empty] | GAAP Q3 2019 rolled forward in 2020 budget and budget reviewed
-23 | 2019-10-30
-22 | 2019-10-31 | SYSTEM | System generated reminder email to BMs | This is the first of a number of automatic emails to prompt Business Managers to view Validation Dashboard and action where appropriate
-21 | 2019-11-01 | XYENTA | Gross Earned Premium posting | The Gross Earned Premium including UA (+UB Sidecar), UJ, UK, UM, UN, UP, UQ & Policy Master File, will be posted by Xyenta. This will be before 9am GMT so that there will be no confliction with other finance Agresso activity |  |  |  | GAAP 2019 Q3 FC Gross & RI Summary (inc BICI) ready
|  | DUBLIN | Earned Premium Controls checked per RCM (refresh FDM post-check control reports at first) | Post Checks refreshed for EPI / Earnings / Binders / QS
-20 | 2019-11-04 | DUBLIN | YTD 31/10 GEP Analysis Prior Yr v Actuals Analysis | October YTD GEP now posted. Comparison with prior year actuals |  |  | Business Manager sign off | GAAP 2020 Budget Gross Summary (inc BICI) ready
-19 | 2019-11-05 |  |  |  | Final postings for 201910 |  | Finance review | GAAP 2020 Budget RI reviewed and RI Summary ready
-18 | 2019-11-06 |  |  |  | 201910 dashboard due
-17 | 2019-11-07 | MI | Summary Q3 Forecast Premium Analysis Sheets Shared with Dublin | Premium summary sheets supporting Q3 Forecast analysis for Exec
|  | MI | YTD 31/10 GEP Analysis Forecast v Actuals Analysis | October YTD GEP now posted. Comparison of actuals with phased Forecast
-16 | 2019-11-08 |  |  |  | Finalise 201910 and open 201911
-15 | 2019-11-11 |  |  |  | 201911 available
-14 | 2019-11-12
-13 | 2019-11-13 | SYSTEM | System generated reminder email to BMs | This is the 2nd of a number of automatic emails to prompt Business Managers to view Validation Dashboard and action where appropriate
|  | MI | PFT v WIZI Ultimate Prm Reconciliation | Current rec performed to ensure PFT and WIZI have ultimate premium aligned for future downstream processes
-12 | 2019-11-14 | MI | Email sent to BMs on validity of Premium Estimate Mth 3 (PFT) | MI to send emails to all Business Managers requesting whether December PFT submitted as part of the Q3 Forecast in October is still valid with current EPI levels up to 13th November known from Tech Hub. Sign -off required of Dec PFT on 18th November. |  |  |  | Wizi updated with Q3 ULRs
-11 | 2019-11-15 | XYENTA | GEP Premium posting + 1E | The Gross Earned Premium including UA "DELTA" (+UB Sidecar), UJ, UK, UM, UN, UP, UQ & Policy Master File, will be posted by Xyenta. This will be before 9am GMT so that there will be no confliction with other finance Agresso activity. The 1E posting will also be posted in 201912 (and reversed in 202001) |  |  |  | 2020 Budget LRs provided
|  | DUBLIN | Earned Premium Controls checked per RCM (refresh FDM post-check control reports at first) | Post Checks refreshed for EPI / Earnings / Binders / QS and Post Checks for 1E
-10 | 2019-11-18 | BM | Signoff Premium Estimate Mth 3 (PFT) | Receipt of sign-off of existing December PFT from BMs (or update provided) |  |  |  | 2019 & 2020 Claims posted
IF NO CHANGE Qtr end month Newest YOA Premium Estimate already in Tech Hub and has ben posted to AGRESSO on 15th November (1E)
|  |  | Sign-off by Management if change to PFT required. | If updates to December PFT are supplied, Finance Management decide on whether material adjustment necessary
|  | DUBLIN | 1E Estimate Analysis inc. 6107 | Full Year Prior-Year comparisons including 1E / 6107 analysis
-9 | 2019-11-19 | [6 empty] | Finalising 2019 Q3 forecast and 2020 budget Q3 Triple (1 person, 1 week)
-8 | 2019-11-20 | DUBLIN | IF new PFT phasing provided and signed off by Management then adjustment posted to AGRESSO (1E) | New Adjustment 1E journal posted to Agresso. This tactical solution is only until PFT v2 is fully Tested in Jan 2020
-7 | 2019-11-21 | DUBLIN | RI Spend (2A) | As per current FDM process
-6 | 2019-11-22 | DUBLIN | GEP Premium posting | The Gross Earned Premium "DELTA" (+UB Sidecar), UJ, UK, UM, UN, UP, UQ & Policy Master File, will be posted by DUBLIN. This is to ensure intraday posting process is known. Normally it is suggested that XYENTA post this DELTA
|  | DUBLIN | Earned Premium Controls checked per RCM (refresh FDM post-check control reports at first) | Post Checks refreshed for EPI / Earnings / Binders / QS and Post Checks for 1E
|  | DUBLIN | Full Year GEP Analysis Prior Yr v Actuals Analysis REFRESHED | November YTD GEP now posted. Comparison of actuals with prior year Actuals - variances highlighted / escalated
|  | DUBLIN | RI Earnings - Non QS RAD & LOD (3G 3H) | As per current FDM process
-5 | 2019-11-25 | DUBLIN | Ult Gross and RI RITC postings per FDM (9A 9B) | As per current FDM process
|  | MI | Full Year GEP Analysis Forecast v Actuals Analysis REFRESHED | Comparison of YTD actuals with Q3 Forecast
-4 | 2019-11-26
-3 | 2019-11-27
-2 | 2019-11-28 | SYSTEM | System generated reminder email to BMs
-1 | 2019-11-29 | BMs | Signoff Validation Dashboard / Last EPI Corrections
|  | PROJECT | Collate business sign-off and complete CGG Control
|  | PROJECT | October/November Actuals compared to October /November PFT using Tech Hub | Provisional Analysis
|  | XYENTA | GEP Premium posting | The Gross Earned Premium including UA "DELTA" (+UB Sidecar), UJ, UK, UM, UN, UP, UQ & Policy Master File, will be posted by Xyenta. This will be before 9am GMT so that there will be no confliction with other finance Agresso activity.
|  | DUBLIN | Earned Premium Controls checked per RCM (refresh FDM post-check control reports at first) | Post Checks refreshed for EPI / Earnings / Binders / QS and Post Checks for 1E
|  | DUBLIN | Full Year GEP Analysis Prior Yr v Actuals Analysis REFRESHED | November YTD GEP now posted. Comparison of actuals with prior year Actuals - variances highlighted / escalated
|  | MI | Full Year GEP Analysis Forecast v Actuals Analysis REFRESHED | November YTD GEP now posted. Comparison of actuals with Q3 Forecast - variances highlighted / escalated
1 | 2019-12-02 | XYENTA | GEP Premium posting | The FINAL Gross Earned Premium including UA "DELTA" (+UB Sidecar), UJ, UK, UM, UN, UP, UQ & Policy Master File, will be posted by Xyenta. This will be before 9am GMT so that there will be no confliction with other finance Agresso activity.
|  | DUBLIN | Earned Premium Controls checked per RCM (refresh FDM post-check control reports at first) | FINAL Post Checks refreshed for EPI / Earnings / Binders / QS and Post Checks for 1E
|  | DUBLIN | Full Year GEP Analysis Prior Yr v Actuals Analysis REFRESHED | FULL YTD GEP now posted. Comparison of actuals with prior year Actuals - variances highlighted / escalated
2 | 2019-12-03 | DUBLIN | Other FDM premium processes |  |  |  | Business Manager sign off
3 | 2019-12-04 | DUBLIN | Other FDM premium processes |  | Final postings for 201911 |  | Finance review
4 | 2019-12-05 |  |  |  | 201911 dashboard due
5 | 2019-12-06
6 | 2019-12-09 |  |  |  | Finalise 201911 and open 201912
7 | 2019-12-10 |  |  |  | 201912 available
8 | 2019-12-11
9 | 2019-12-12
10 | 2019-12-13
11 | 2019-12-16
12 | 2019-12-17
13 | 2019-12-18
14 | 2019-12-19
15 | 2019-12-20
16 | 2019-12-23 |  |  |  | Final postings for 201912
17 | 2019-12-24 |  |  |  | 201912 dashboard due
18 | 2019-12-27 |  |  |  | Finalise 201912??
19 | 2019-12-30
20 | 2019-12-31
21 | 2020-01-02
22 | 2020-01-03 |  |  |  | assess if additional postings required (investments/FX) |  | Business Manager sign off
23 | 2020-01-06 |  |  |  |  | Load any final postings | Finance review
24 | 2020-01-07 |  |  |  | Finalise 201912 | Dashboard due (for changes)
25 | 2020-01-08
Finalise 201912