## Handover Doc
Artefacts
[7 empty] | Business Process Documentation |  |  |  | FDM Documentation |  |  | Overall Status/Comment | Documentation /Folder Link
Original POAP # | POAP # | Process /Entity Name/Activity | Sub processes/ FDM Modules | Stakeholders | Process Owner | Resource | Process Overview | POAP | Process Flow | Risk and Control Matrix (WCGW) | FDM Inputs, Process and Outputs | FDM User Process Checklist | FDM Process Guides
1 | 1 | Expenses | Expense Allocations | Courtney Maratta | Christopher Heath | Cosmas | ü | ü | ü | ü | ü | ü | n/a | Complete. Awaiting final process owner sign off | W:\Finance\Projects\RCM\1. Expenses
|  |  | DAC | Christopher Heath | Christopher Heath | Cosmas | n/a | n/a | n/a | n/a | ü | ü | n/a | Complete Awaiting final process owner sign off
2 | 2 | Investments and Capital | Investments Reporting | Hussein Affi Rebecca Thickbroom Ryan Price | Ryan Price | Cosmas | ü | ü | ü | ü | n/a | n/a | n/a | Complete. Documentation completed by users. No FDM modules | W:\Finance\Projects\RCM\2. Investments
|  |  | Investment Triggers | Ryan Price | Ryan Price | Cosmas | ü | ü | ü | ü | ü | ü | n/a | Complete
4 |  |  | Capital | Kathryn Edwards | Kathryn Edwards | Juliet | In Progress | In Progress | In Progress | In Progress |  |  | n/a | In progress. No FDM modules | W:\Finance\Projects\RCM\4. Capital
3 | 3 | Treasury and Cash Management | Cash and Treasury Management | Kathryn Edwards | Kathryn Edwards | Juliet | ü | ü | ü | ü | n/a | n/a | n/a | Complete. No FDM modules. Final business sign off outstanding. | W:\Finance\Projects\RCM\3. Treasury and Cash Management
5 | 4 | Premiums | Eurobase/US EPI Binder Adjustment Gross Ultimate Adjustment EPI Adjustment Earnings | Bob Sherlock Dublin Syndicate Finance team | Niall Lillis | Cosmas | ü | ü | ü | ü | ü | ü | n/a | Complete | W:\Finance\Projects\RCM\5. Premiums
7 |  |  | RITC | Dublin Finance | Niall Lillis | Cosmas | ü | ü | ü | ü | ü | ü | n/a | Complete | W:\Finance\Projects\RCM\7. RITC
6 | 5 | Claims | Claims | Coverholder Finance Dublin Finance | Niall Lillis | Cosmas | ü | ü | ü | ü | ü | ü | n/a | Complete | W:\Finance\Projects\RCM\6. Claims
8 | 6 | Reinsurance |  | Dublin Finance | Daragh Brennan | Cosmas | ü | ü | ü | ü | ü | ü | n/a | Complete | W:\Finance\Projects\RCM\8. Reinsurance
|  |  | BeRe QS | Rachael Ward | Niall Lillis | Cosmas | n/a | n/a | n/a | n/a | ü | ü | n/a | Complete
|  |  | Korean Re | Daragh Brennan | Daragh Brennan | Cosmas | n/a | n/a | n/a | n/a | ü | ü | n/a | Complete
10 | 7 | Tax |  | Gregor Szpin | Gregor Szpin | Juliet | In Progress | In Progress | In Progress | In Progress | n/a | n/a | n/a | In progress .No FDM modules | W:\Finance\Projects\RCM\10. Tax
11 | 8 | Internal Reporting/Management Information | Budgeting and Forecasting | Tom McCaw Steve Rayment | Steve Rayment | Daniel | Not started | ü | Not started | Not started | n/a | n/a | n/a | In progress. MI team resource availability issues slowed progress on this. No FDM modules | W:\Finance\Projects\RCM\11. Internal Reporting
|  |  | Internal Model Finance Sign off | Finance and Risk | Kathryn Edwards | Cosmas | ü | ü | ü | ü | n/a | n/a | n/a
|  |  | MI Reporting | Tom McCaw Steve Rayment | Steve Rayment | Cosmas | Not started | ü | Not started | Not started | n/a | n/a | n/a
12 | 9 | Group Reporting |  | Elena Lobacheva | Stuart Johnson | Cosmas | ü | ü | ü | ü | n/a | n/a | n/a | Complete. No FDM modules. Final business sign off outstanding. | W:\Finance\Projects\RCM\12. Group Reporting
|  |  | General Ledger Maintenance Proposed process | Elena Lobacheva | Stuart Johnson | Cosmas | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Draft proposal completed. Ownership could not be agreed and work was put on hold
|  |  | FX Excelerators | FDM Developers Group Finance | Stuart Johnson | Cosmas | n/a | n/a | n/a | n/a | ü | ü | n/a | Complete
13&14 | 10 | Regulatory Reporting | CBI | Rizwan Kermali | Kathryn Edwards | Cosmas | ü | ü | ü | ü | n/a | n/a | n/a | Complete. No FDM modules. | W:\Finance\Projects\RCM\14. Regulatory Reporting
|  |  | Lloyds | Rizwan Kermali | Kathryn Edwards | Cosmas | ü | ü | ü | ü | n/a | n/a | n/a
|  |  | Syndicate Reporting | Dublin Finance | Daragh Brennan | Cosmas | ü | ü | ü | ü | n/a | n/a | n/a
|  |  | QMA and QMR Reporting Requirements/Analysis | Rizwan Kermali | Daragh Brennan | Cosmas | ü | ü | ü | ü | n/a | n/a | n/a
| n/a | European Insurance Company (EIC) | Premium/ Accounts Receivables | EIC Programme/Finance | Declan Lynch | Cosmas |  |  | ü |  | Not started | Not started | n/a | High level process and data flows and associated journal entries completed for each of the processes. | W:\Finance\Projects\RCM\EIC Work
|  |  | Claims | EIC Programme/Finance | Declan Lynch | Cosmas |  |  | ü |  | Not started | Not started | n/a
|  |  | Expenses | EIC Programme/Finance | Declan Lynch | Juliet Cosmas |  |  | ü |  | Not started | Not started | n/a
| n/a | Singapore | Premium/ Accounts Receivables | Singapore Finance | Mary- Anne Loo | Cosmas | n/a | n/a | ü | n/a | Not started | Not started | n/a | High level process and data flows and associated journal entries completed for each of the processes. | W:\Finance\Projects\RCM\Singapore
|  |  | Claims | Singapore Finance | Mary- Anne Loo | Cosmas | n/a | n/a | ü | n/a | Not started | Not started | n/a
|  |  | Expenses | Singapore Finance | Mary- Anne Loo | Juliet Cosmas | n/a | n/a | ü | n/a | Not started | Not started | n/a
|  |  | FDM Data Inputs and Sources | Singapore Finance | Mary- Anne Loo | Cosmas | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Analysis of FDM data inputs and sources
|  |  | High Level Agresso and FDM Business Requirements | Singapore Finance | Mary- Anne Loo | Cosmas | n/a | n/a | n/a | n/a | n/a | n/a | n/a | High level Singapore requirements split into those to be delivered via Agresso and those via FDM.
| n/a | POAP Level Risk and Control Matrix | All | Finance and Risk | Finance and Risk | Cosmas | n/a | n/a | n/a | ü | n/a | n/a | n/a | Complete. Recommended risk register updates shared with Risk team to update the Risk register | W:\Finance\Projects\RCM\Risk Register Update
|  | Entity Level Controls | All | Finance and Risk | Finance and Risk | Cosmas Juliet Daniel | n/a | n/a | n/a | ü | n/a | n/a | n/a
|  | General Computer Controls | All | Finance and Risk | Finance and Risk | Cosmas Rob | n/a | n/a | n/a | ü | n/a | n/a | n/a
| n/a | FDM Core Processes | FDM Posting Engine | FDM Developers | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | ü | Various documentation current and proposed FDM processes and data analysis and recommendations for optimisation
|  |  | Run FDM Processes | FDM Developers | n/a | Cosmas | n/a | n/a | n/a | n/a | n/a | n/a | ü |  | W:\Finance\Projects\RCM\FDM Documentation
|  |  | Future FDM Access Management Model |  |  | Cosmas | n/a | n/a | n/a | n/a | n/a | n/a | ü
|  |  | FDM Issues Analysis |  |  | Cosmas | n/a | n/a | n/a | n/a | n/a | n/a | ü
|  |  | Access to FDM control sheet |  |  | Cosmas | n/a | n/a | n/a | n/a | n/a | n/a | ü
|  |  | FDM System Notifications/Alerts |  |  |  | n/a | n/a | n/a | n/a | n/a | n/a | ü
|  |  | FDM External data inputs and Destinations Accounts Mapping |  |  | Cosmas | n/a | n/a | n/a | n/a | n/a | n/a | ü
|  |  | FDM Components and Modules using the components |  |  | Cosmas | n/a | n/a | n/a | n/a | n/a | n/a | ü
|  |  | FDM External data inputs Process Redesign for p process Optimisation | [7 empty] | n/a | n/a | ü
|  |  | FDM Data & Modules Dependency Flows/Matrix | FDM Developers | n/a | Cosmas | n/a | n/a | n/a | n/a | n/a | n/a | ü
|  | Other FDM Modules user checklists | FX Non Monetary Adjustment | Rachael Ward | Niall Lillis | Cosmas | n/a | n/a | n/a | n/a | ü | ü | n/a |  | W:\Finance\Projects\RCM\Other FDM Modules User Docs
|  |  | 263 Profit Commission | Daragh Brennan | Daragh Brennan | Cosmas | n/a | n/a | n/a | n/a | ü | ü | n/a
|  | Syndicate Period Timetable Analysis and Streamline proposal | Syndicate Reporting |  |  | Cosmas | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Timetable is also in Wrike | W:\Finance\Projects\RCM\Finance Timetables
|  | Syndicate Period Timetable Analysis and Streamline proposal | Syndicate Reporting |  |  | Cosmas | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | W:\Finance\Projects\RCM\Finance Timetables
|  | Finance Workflow Design Proof of Concept | Syndicate Reporting |  |  | Cosmas | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | W:\Finance\Projects\RCM\Finance Workflow POC